## Sheet (hidden)
Project Task | Task Owner | Estimated Days | Start Date | End Date | Comments | Status
Prerequisite |  | 2
KO Call | Hanu | 1
Technical Discovery sessions | Hanu and Nykaa | 1
Implementation Phase |  | 9
MVC Setup | Hanu | 1
Verify Domain in Azure AD | Hanu | 1
Run AD connect to sync on-prem users with Azure AD | Hanu and Nykaa | 1
Deploy Fortigate in azure | Hanu | 2
Site to Site connection with their on-prem network | Hanu and Nykaa | 2
Extend their On-prem ADC to azure | Hanu and Nykaa | 1
Create a Storage account ( Prem/ Stand) with private endpoint | Hanu | 1
Create a File share | Hanu
Create Directory inside the Azure File Share | Hanu
Enable Active Directory Authentication with Azure Storage Account | Hanu
Assign RBAC to the Specified User’s | Hanu
Assign ACL permission to the User’s Group | Hanu
Setting up Azure File Sync Service between On-Premise file Server to Azure File Share |  | 5
Deploy the Storage Sync Service | Hanu and Nykaa
Prepare Windows Server to use with Azure File Sync | Hanu and Nykaa
Install the Azure File Sync agent on the On-premise file server | Hanu and Nykaa
Register the on-premise server with Azure file Sync | Hanu and Nykaa
Create a sync group and a cloud endpoint | Hanu
Create a server endpoint | Hanu
Sync the Data from on-premise to Azure File Share | Hanu and Nykaa
Once the Data are synced to Azure, remove the Server Endpoint | Hanu and Nykaa
Setting up Azure File Share backup |  | 1
Create Azure Site recovery vault | Hanu | 1
Setting up Backup for Azure File Share | Hanu
Define the Backup policy as per the BOM | Hanu

## ProjectPlan
Milestones | Project Tasks | Task Owner | Status | Actual Start Date | Actual Completion Date | Comments
Milestone 1
| Setup KO Call with Customer | Hanu&NYKAA | To-Do
| Hanu Team will be creating a new Subscription under existing D365 Tenant of Nykaa Fashion | Hanu | To-Do
| Grant NYKAA Azure subscription access to project team | NYKAA
| Complete On-prem File Server, FortiGate FW site-site Questionnarie and discuss naming convention | NYKAA | To-Do
| Share naming convention document with customer | Hanu | To-Do
Milestone 2 | Implementation Central-India
| Create Resource Group | Hanu | To-Do
| Create Virtual Networks and peerings(if required) -->(Discuss about the Vnet CIDRS with Nykaa team) | Hanu
| Create Subnets | Hanu
| Extend their On-prem DC to Azure | Hanu
| Deploy Azure Storage account and file shares (Approx 5-6 TB) | Hanu
| Domain join the storage account (Ask Nykaa team for domain admin creds) | Hanu
| Deployed one FortiGate firewall (create dedicated subnet for the FW) | Hanu
| Deploye site-site connection from on-prem FortiGate FW to Azure FortiGate Firewall | Hanu
Milestone 3
| Verify Domain in Azure AD | Hanu | To-Do
| Run AD connect to sync on-prem users with Azure AD | Hanu | To-Do
| Sync the User’s group to Azure Active directory using Soft match ( 10 users according to SOW) | Hanu | To-Do
Milestone 4
| Set necessary permission on azure file share (SMB file share storage contributor) | Hanu/NYKAA | To-Do
| Create DNS Zone /forwarder on Active Directory | Hanu | To-Do
| Deploy the Storage Sync Service | Hanu | To-Do
| Install the Azure File Sync agent on the On-premise file server | Hanu /NYKAA | To-Do
| Register the on-premise server with Azure file Sync | Hanu /NYKAA | To-Do
| Create a sync group and a cloud endpoint | Hanu | To-Do
| Create a server endpoint | Hanu | To-Do
| Sync the Data from on-premise to Azure File Share | Hanu | To-Do
| Once the Data are synced to Azure, remove the Server Endpoint | Hanu | To-Do
Milestone 5
| Create Azure Site recovery vault | Hanu | To-Do
| Setting up Backup for Azure File Share | Hanu | To-Do
| Define the Backup policy as per the Client requirement | Hanu/NYKAA | To-Do
Milestone 6
| Provisioning of access to all users | Hanu /NYKAA | To-Do
| User testing for the working status of Fileshare | NYKAA | To-Do
Milestone 7
| Assistance in the resolution of users issue | Hanu | To-Do

## Efforts estimate
Milestones | Project Tasks | Task Owner | Status | Est. Lead Efforts (Hrs) | Est. Engg. Efforts (Hrs) | Scrum Ceremonies/ProjectManagement/Meetings Efforts (hrs) | Total Efforts (Hrs) | Assumptions/Comments
Milestone 1
| Setup KO Call with Customer | Hanu&NYKAA | To-Do
| Setup PAL association for Nykaa | Hanu | To-Do
| Hanu Team will be creating a new Subscription under existing D365 Tenant of Nykaa Fashion | Hanu | To-Do
| Grant NYKAA Azure subscription access to project team | NYKAA | To-Do
| Complete On-prem File Server, FortiGate FW site-site Questionnarie and discuss naming convention | NYKAA | To-Do
| Share naming convention document with customer | Hanu | To-Do
Milestone 2 | Implementation Central-India |  |  | 12 | 40 |  | 52
| Create Resource Group | Hanu | To-Do
| Create Virtual Networks and peerings(if required) -->(Discuss about the Vnet CIDRS with Nykaa team) | Hanu | To-Do
| Create Subnets | Hanu | To-Do
| Extend their On-prem DC to Azure | Hanu | To-Do
| Deploy Azure Storage account and file shares (Approx 5-6 TB) | Hanu | To-Do
| Domain join the storage account (Ask Nykaa team for domain admin creds) | Hanu | To-Do
| Create pvt endpoint | Hanu | To-Do
| Create conditional forwarder on prem | Hanu | To-Do
| Deployed Fortinet FortiGate Next-Generation Firewall (create dedicated subnet for the FW) | Hanu | To-Do
| Deploye site-to-site connection from on-prem FortiGate FW to Azure FortiGate Firewall | Hanu | To-Do
Milestone 3 |  |  |  | 9 | 30 |  | 39
| Verify Domain in Azure AD | Hanu | To-Do
| Run AD connect to sync on-prem users with Azure AD | Hanu | To-Do
| Sync the User’s group to Azure Active directory using Soft match | Hanu | To-Do
Milestone 4 |  |  |  | 9 | 30 |  | 39
Set necessary permission on azure file share (Storage File Data SMB Share Elevated\Contributor)
| Deploy the Storage Sync Service | Hanu | To-Do
| Install the Azure File Sync agent on the On-premise file server | Hanu /NYKAA | To-Do
| Register the on-premise server with Azure file Sync | Hanu /NYKAA | To-Do
| Create a sync group and a cloud endpoint | Hanu | To-Do
| Create a server endpoint | Hanu | To-Do
| Sync the Data from on-premise to Azure File Share | Hanu | To-Do
| Once the Data are synced to Azure, remove the Server Endpoint | Hanu | To-Do
Milestone 5 |  |  |  | 3 | 10 |  | 13
| Create Azure Site recovery vault | Hanu | To-Do
| Setting up Backup for Azure File Share | Hanu | To-Do
| Define the Backup policy as per the Client requirement | Hanu/NYKAA | To-Do
Milestone 6 |  |  |  | 3 | 10 |  | 13
| Provisioning of access to all users | Hanu /NYKAA | To-Do
| User testing for the working status of Fileshare | NYKAA | To-Do
Milestone 7
| Assistance in the resolution of users issue | Hanu | To-Do

## Sheet1 (hidden)
Action Item | Owner | Start Date | Completion Date | Priroty | Action Taken | Comment
KO Call | To be Started
Discovery Session-I •Questionnarie Shared •Onboard Hanu SMEs on Azure/Onprem •Network Topology •Inventory Sheet | To be Started
To be Started
To be Started
Completed
Foundational Service Setup
Hanu Team will be creating a new Subscription under existing D365 Tenant of Nykaa Fashion | To be Started
Defining Resource Groups
In Progress
Identity and Access Management
Role Based Access Control (RBAC) definitions | In Progress
Azure AD Setup | Completed
Completed
Prepare Networking
Creation of Azure Virtual Network
Creation of FortiGate NVA
Creation of Site to Site VPN from on-premise to Azure between 3-4 location.
Create Network Security Groups
In Progress
Azure Active Directory Setup | In Progress
Install Azure AD connect on the on-premise Server
Sync the User’s group to Azure Active directory using AD connect
Setting up Additional Domain Controller on Azure (Optional)
Promote Additional domain controller on Azure
Define the DNS on the Azure Subnet
Setting up Azure File Share with Active Directory Authentication
Create an Azure Storage Account
Create an Azure File Share
Create Directory inside the Azure File Share
Enable Active Directory Authentication with Azure Storage Account
Assign RBAC to the Specified User’s
Assign ACL permission to the User’s Group
Create Private Endpoint for Azure File Share to Secure the Access
Setting up Azure File Sync Service between On-Premise file Server to Azure File Share
Deploy the Storage Sync Service
Prepare Windows Server to use with Azure File Sync
Install the Azure File Sync agent on the On-premise file server
Register the on-premise server with Azure file Sync
Create a sync group and a cloud endpoint
Create a server endpoint
Sync the Data from on-premise to Azure File Share
Once the Data are synced to Azure, remove the Server Endpoint
Setting up Azure File Share backup
Create Azure Site recovery vault
Setting up Backup for Azure File Share
Define the Backup policy as per the BOM